## Slide 1
Sharing Insight and Experience from an Alma Implementation
Mike Rogers
University of Tennessee
Keynote Address, eBUG 2015 – Lexington, KY

## Slide 2: For today’s talk…
UT Library and our path to Alma
Overview of Alma implementation process
Tips for staying sane during implementation
Pros/Cons of moving to Alma
Final Thoughts – now and the future

## Slide 3: UT Library and our path to Alma

## Slide 4: University of Tennessee Library:
One main library, three branch libraries
150 library staff (48 faculty librarians)
Serves 26,000+ students, 9,000+ faculty/staff
UT Medical Library holdings are in catalog
On-campus storage facility

## Slide 5: Enterprise Systems Prior to Alma
Aleph
  Implemented Fall 2003
Primo
  Implemented Fall 2009
SFX
  Implemented Fall 2002
ILLiad
  Implemented pre-2000

## Slide 6: Systems mindset dilemma: Early adoption vs. behind the curve?

## Slide 7: 2013 – the year it started
Administrative push to cease server hosting
Departmental restructuring
  Enterprise Systems integrated with Technical Services to become “Discovery & Technical Services”
Maribeth Manoff (Dept. Head) charged by Dean to investigate next-generation library systems
April 2013 – Carl Grant visit to UT Library
May 2013 – ELUNA, Athens GA
July & August – In-house demos of ExLibris’ Alma and OCLC’s Worldshare Management Services
Sep through Dec – RFP for new system

## Slide 8: Spring 2014
January
  signed contract w/ ExLibris for Alma
  Met w/ ExLibris Sales and Professional Services staff at ALA Mid-winter
  Began reviewing “Getting Ready for Alma” doc
April
  Pre-kickoff meeting
  Filled out & submitted Alma Implementation form
  Appointed Implementation team members
  Met briefly with ExLibris staff at ELUNA (Montreal)
May
  Exchanged some emails w/ ExLibris project manager

## Slide 9
June 12, 2014 – Kickoff Meeting!
WebEx phone call between ExLibris and University of Tennessee

## Slide 10
Overview of Alma Implementation Process

## Slide 11: UT Project Team
Project Manager
Technical Lead/Overall Data Expert
Data Expert, Acquisitions & E-Resources
Data Expert, Fulfillment
Data Expert, Resource Management
Functional Expert, Acquisitions (2)
Functional Expert, E-Resources (2)
Functional Expert, Fulfillment (2)
Functional Expert, Resource Management
Functional Expert, Primo

## Slide 12: ExLibris Project Team
Project Manager
Alma Implementation Consultant
Alma Technical Lead
Alma “Knowledge Guru”
Primo Consultant
Infrastructure Consultant
Various Alma, Primo, & Networking Experts

## Slide 13: Communication methods
Basecamp
  Project management software (desktop & mobile)
  Topical threads
  Document storage
Weekly status phone calls
  WebEx
E-mail (lots of email…)
Phone calls
Two on-site visits
  Configuration Form overview
  2 day Alma Workshop

## Slide 14: In spite of all these communication methods, the lack of face-to-face communication can be difficult during the implementation process

## Slide 15: UT’s schedule:
Six month process from Kickoff Meeting to Go-Live
Weekly status phone calls between site & ExLibris
Ongoing recorded trainings and Q&A for first 3 months
Sandbox access provided early on
Migration Form, P2E file, 1st Auto-extract due approx. five weeks after Kick-off
Onsite configuration meeting July 21-22
Configuration form due August 8

## Slide 16: UT’s schedule (cont.)
Test load / production env. delivered August 18
Primo delivered for testing September 15
Data checking August – October
Ongoing data clean-up in old system (e.g. Aleph)
Certification training during month of November
Cutover activities and final data extraction during December 8-17
Go Live December 18

## Slide 17: Alma Reports & Analytics Training
WebEx Training Session (not on-site)
  UT had multiple attendees
  ExLibris trainer was excellent, with very relevant material
2 days:
  Day 1 – Strategies and techniques for using Alma to perform record batch work, data cleanup, etc
  Day 2 – Analytics reporting
Training occurred in the 3rd month of our Implementation

## Slide 18: Certification Training
In-depth online training for Alma administrators
  UT had four staff receive training
4-weeks:
  Week 1 – User management (~3 hours videos)
  Week 2 – Fulfillment (~10+ hours of videos)
  Week 3 – Resource Management (~6+ hours videos)
  Week 4 – Review & Exam
Training occurs near the end of 6-month implementation
Once certified, staff are allowed access to Alma configuration

## Slide 19: Feedback on Training & Certification
Training is very in-depth, very helpful
Primary trainers are excellent
  Connie Braun (Reports & Analytics)
  Shmuel Moss (Certification)
Overall we learned a LOT
but …
Strong consensus was that Certification Training should have occurred much earlier in process
Felt that Analytics training would have been more helpful towards the end of the Implementation process

## Slide 20: Final Cutover & Downtimes
Technical Services: December 7 – 17
  11 days downtime
Fulfillment (Circulation): December 16 – 17
  2 days downtime
  Staff used Offline Circulation

## Slide 21: Trivia Time #1!
Name the U.S. state where both Abraham Lincoln (President of the Union) and Jefferson Davis (President of the Confederacy) were born?
Answer:
*they were born less than 100 miles and one year apart

## Slide 22: Tips for Staying Sane During Implementation

## Slide 23: Tip #1 – Begin working prior to the Kick-Off Meeting

## Slide 24: What to do prior to kickoff?
Learn as much as you can about Alma
  Ask other Alma customers
  Push ExLibris for as much information as you can get
Start data clean-up (consult colleagues, work with pre-Implementation Consultant)
Communicate with library staff
Map out workflows
Stay calm!

## Slide 25: Tip #2 – Change your mindset about the concept of “implementation”

## Slide 26: Very Important to Understand…
“Go Live” does not mean 100% implementation
Rather, you are simply running Alma in live mode, performing bulk of work on new system
Three system migrations in one
  Integrated Library System (ILS)
  Discovery system (Primo)
  Link Resolver

## Slide 27: Comparison of system migrations (UT):
Geac to Horizon (1997) – 6 months
Horizon to Aleph (2003) – 8 months
SFX (2002) – 1 to 2 months
Primo (2009) – 6 months
Result = Very complex migration in limited amount of time!
Aleph/SFX/Primo to Alma/Primo – 6 months

## Slide 28: Tip #3 – Expect the unexpected

## Slide 29: Things can and do go wrong during Implementation
Unexpected data migration issues
Staff departures
Misunderstandings between site and ExLibris, e.g.
  Scheduling differences
  Communication about deliverables
Server crash on legacy ILS, causing an Oracle array puncture and loss of data right in the middle of Implementation, requiring 2 weeks recovery
Yes, this happened to us!

## Slide 30: Tip #4 – Acknowledge progress made and milestones reached … and take time out for “breaks”

## Slide 31
*Project Manager purchased T-shirts to celebrate a successful implementation

## Slide 32
Find your stream ….
…. and relax

## Slide 33: Tip #5 - Give constructive feedback to ExLibris as necessary

## Slide 35: Constructive feedback can include:
What is/isn’t working well
Suggestions for improvement
What your expectations were, and how the outcomes differed
*Feedback can be very beneficial both to ExLibris (as they improve the migration process) as well as future Alma customers (who benefit from the improvements made).

## Slide 36
Ultimately …
ExLibris wants your project to succeed just as much as you do

## Slide 37: Tip #6 – Remind your staff (and yourself) to take things one day at a time

## Slide 38: Although it feels like a sprint, implementing Alma should be treated like a marathon

## Slide 39: Trivia Time #2!
During the 1970s, three different horses won the Triple Crown. What were the names of the three horses?
Secretariat (1973)
Seattle Slew (1977)
Affirmed (1978)
Answer:

## Slide 40: Pros & Cons of Moving to Alma

## Slide 41: Pros
Cloud-based, multi-tenancy system
  No more hardware or server maintenance
  Web access means no GUI clients to install/maintain
  No more version upgrades, service packs, or hot packs performed by the customer
  Much more rapid update process (monthly)
  No more re-indexing by site
Little to no downtime
  Apart from routine overnight maintenance, we’ve experienced zero downtime in the past seven months

## Slide 42: Pros (cont.)
Essentially eliminated after-hours “on call” for systems staff
Alma as a system seems very integrated
  Move away from a modular-type system
  Integrated workflows
  Integrated Analytics: can embed custom reports into user dashboards
Excellent record loading functionality
  Powerful and flexible loading templates
  Scheduling
  Good match profiling

## Slide 43: Pros (cont.)
Very active and helpful user community
Community Zone – much future potential
  Ongoing updates to e-resources
  Shared cataloging records
APIs available for creating custom read/writes to the data
Many results screens in Alma allow for direct Excel dumps
Our experience with Alma Support has been very positive

## Slide 44: Pros (cont.)
Integrated Analytics provides much better reporting capabilities
Much better integration with Primo
  OPAC via Primo
  Customized request screen using a “Discovery Skin”
  User’s loan policy details appear after sign-in
  OpenURL links to ILLiad for Interlibrary Loan requests
Normalization rules for cataloging updates and record loading are powerful and accessible to staff
Often a very good exercise to re-evaluate library processes & workflows in the context of a migration

## Slide 45: Cons
It is a LOT of work to migrate
  Essentially migrating your ILS and Link Resolving system to Alma
  Implement (or re-implement) Primo
  Much work beyond 6 month migration period
Pricing is expensive
As a “young” system, some functionality and/or workflow options still missing from Alma
Must wait on enhancement process to see significant system changes driven by customers

## Slide 46: Cons (cont.)
No more direct access to back-end database
Learning curve for administrators & staff
Potential for stress amongst individuals, departments, etc. due to change
Third-party integrations are not well integrated … onus on customer to configure these
  SAP
  Banner
  Patron import

## Slide 47: Cons (cont.)
Alma error messages often terse and unclear; system troubleshooting by customer is limited
  Probably by design, but customers used to solving problems more quickly on their own are now more dependent on SalesForce
Limitations in Analytics hamper certain reporting situations
  Limitation on # of input rows for a query
  Limitation on # of rows exportable to Excel
Certain system jobs are not flexible when it comes to scheduling

## Slide 48: Pros or cons? You decide.
No more traditional printing in Alma
  All printing is done through e-mail
Alma Configuration setup is an ongoing process
  We are still configuring Alma 6 months past implementation
Strongly encouraged to setup loan rules “fresh” rather than trying to replicate legacy rules in Alma
  Good way to eliminate duplication in codes/setup
  Means more work at beginning

## Slide 49: Final Thoughts: Where are we today? What is in store for the future?

## Slide 50: Today we are:
Cleaning up migration problems
Preparing for first fiscal year rollover
Re-implementing 3rd party integrations
  Alma-to-SAP (invoice transfer)
  Alma-to-Banner (holds & fines transfer)
Working with subject librarians on custom reports
User-centered custom programs
  Carrel reservation system
  New books pages
Creating a missing items workflow

## Slide 51: Future work includes:
Leveraging the community zone for shared cataloging
Authority control
Greatly increasing Analytics reporting
  ARL stats
  Campus reports
Better integration between Alma & ILLiad (NCIP protocol)
Gathering feedback on patron enhancements and custom programming

## Slide 52
But I wonder … what will it look like for a site to migrate from Alma to another vendor’s system?

## Slide 53: In summary:
Alma is an amazing system with a ton of potential
Alma is expensive and a lot of work to implement … but we felt it was worth the effort
Our systems unit has been freed up from general systems overhead and maintenance tasks in order to focus more on patron and staff needs
Sites considering Alma should carefully weigh the pros and cons, and gather feedback from existing customers

## Slide 54
Thank you for your attention!
Any questions?
mikerogers@utk.edu