## FMECA Tracks (Drive)
Failure Mode, Effects, and Criticality Analysis (FMECA) of Tracks Sub-System
[9 empty] | FMEA No. | [5 empty] | ME-DR-1
|  |  | Sub-system: | Tracks |  |  | P = Probability of Occurrence |  | Final Design Deadline: | [5 empty] | 2010-05-03
|  |  | System: | A.R.T.E.M.I.S. PRIME Lunar Excavator |  |  | S = Severity of Failure Effect |  | Prepared by: | [5 empty] | Amanda Huff
|  |  | Design Responsibility: | ME Sub-Team: C. Gries, A. Huff, W. Tyree |  |  | D = Probability of Detection |  | FMEA Date (Orig.) | [5 empty] | 2010-05-18
[7 empty] | RPN = Risk Priority Number |  | FMEA Date (Rev.) | [5 empty] | 2010-07-24
Assessment Number |  |  | Component / Subsystem Name | Function | Potential Failure Mode(s) | Potential Effect(s) of Failure | Potential Cause(s) / Mechanisms of Failure | Current Controls (Prevention) | Current Controls (Detection) | Risk Assessment |  |  |  |  | Recommended Action(s) | Responsibility | Action(s) Taken | Revised Risk Assessment
[10 empty] | P | S | D | RPN | PV |  |  |  | P | S | D | RPN | % RPN Reduction | PV | % PV Reduction
DR - | 1 | a.1 | Control System (Wiring) | Control track motors | Device not actuated | Failure to lift | No power due to faulty electrical connections | Supervision / review by advisor proir to implementation of electrical control system | Device testing | 4 | 7 | 4 | 112 | 16 | Repair Connections | EE sub-team | Connections repaired prior to competition | 2 | 7 | 4 | 56 | 50% | 8 | 50%
DR - | 1 | a.2 | (Wiring) |  |  |  | Failure to execute desired function due to faulty electrical connections |  |  | 5 | 7 | 5 | 175 | 25 | Repair Connections | EE sub-team | Connections repaired prior to competition | 2 | 7 | 5 | 70 | 60% | 10 | 60%
DR - | 1 | a | [7 empty] | Item RPN & PV |  |  | 287 | 41 |  |  |  | Item RPN & PV |  |  | 126 | 56.1% | 18 | 56.1%
DR - | 1 | b | (Battery) | Control track motors |  |  | No power due to battery charger malfunction |  | Monitor charging battery | 2 | 7 | 5 | 70 | 10 | Rectify charger issue; charge battery | EE sub-team | N/A | 2 | 7 | 5 | 70 | 0% | 10 | 0%
DR - | 1 | c | (Code) |  |  |  | Failure to execute desired function due to incorrect code (progamming issue) | Supervision / review by advisor proir to implementation of electrical control system | Device testing | 5 | 7 | 5 | 175 | 25 | Revise Code | EE sub-team | Code revised prior to competition | 1 | 7 | 5 | 35 | 80% | 5 | 80%
DR - | 1 | d | (Interface) |  |  |  | Mistake by operator at human-machine interface (HMI) | Practice under competition-simulated conditions | Observaton (during device testing / practice) | 6 | 1 | 1 | 6 | 6 | Continued Practice | C. Gries | Gries practiced both at WKU and at Kennedy as able | 2 | 1 | 1 | 2 | 66.67% | 2 | 66.67%
DR - | 1 | e.1 | (Robot-Solutions RS80D Motor Controller) |  | Correct commands not sent to motor | Failure to drive | Motor controller fault | Supervision / care taken during operation | Device testing | 3 | 7 | 1 | 21 | 3 | Replace / repair controller. Determine cause of fault and take action to prevent recurrence | EE sub-team | N/A | 3 | 7 | 1 | 21 | 0% | 3 | 0%
DR - | 1 | e.2 |  |  | Track motors unintentinally set at full speed | Inability to stop tracks | Controller locked in "on" mode due to inactivity of controller code | Emergency stop implemented |  | 8 | 10 | 1 | 80 | 8 | Revise to send "stop" command often enough to keep motor controller active | EE sub-team | Code revised to send "stop" command often enough to keep motor controller active | 2 | 10 | 1 | 20 | 75% | 2 | 75%
DR - | 1 | e | [7 empty] | Item RPN & PV |  |  | 101 | 11 |  |  |  | Item RPN & PV |  |  | 41 | 59.41% | 5 | 54.55%
DR - | 1 | f | (CSD Controller Board) | Command motor controller | Correct commands not sent to motor controller | Failure to lift | Controller board fault | Supervision / care taken during operation | Device testing | 4 | 7 | 1 | 28 | 4 | Replace / repair board. Determine cause of fault and take action to prevent recurrence | EE sub-team | Board replaced prior to competition | 6 | 7 | 1 | 42 | -50% | 6 | -50%
DR - | 1 | [8 empty] | Electrical RPN & PV |  |  | 667 | 97 |  |  |  | Electrical RPN & PV |  |  | 316 | 52.62% | 46 | 52.58%
DR - | 2 | a | Track Motors | Move Tracks | Functional Device Failure | Failure to drive | Overload | Derating of motors | Device Testing | 5 | 8 | 2 | 80 | 10 | Repair motor(s); decrease load; if necessary purchase new motors with increased power capabilities | EE sub-team; ME sub-team | N/A | 5 | 8 | 2 | 80 | 0% | 10 | 0%
DR - | 2 | b |  |  |  |  | Fatigue |  |  | 3 | 8 | 3 | 72 | 9 |  | EE sub-team; ME sub-team | N/A | 3 | 8 | 3 | 72 | 0% | 9 | 0%
DR - | 2 | c |  |  | Motors running at different speeds | Curved path for tracks | Incorrect code for motor speeds |  | Device Testing | 5 | 4 | 1 | 20 | 5 | Modify code | EE sub-team | Conducted limited testing to determine appropriate PWM values (for motor speeds); modified code accordingly | 5 | 4 | 1 | 20 | 0% | 5 | 0%
DR - | 2 | [8 empty] | Item RPN & PV |  |  | 172 | 24 |  |  |  | Item RPN & PV |  |  | 172 | 0% | 24 | 0%
DR - | 3 |  | Gears | Reduce speed, increase torque | Interference | Damage to gears | Misalignment | Modification to supplied mounting plate | Device testing | 4 | 1 | 9 | 36 | 36 | Additional mounting plate modification | ME sub-team | N/A | 4 | 1 | 9 | 36 | 0% | 36 | 0%
DR - | 4 | a | Support Rods | Support Load | Yielding failure | Warping of overall track structure | Overload | Derating of tracks | Device Testing | 2 | 2 | 1 | 4 | 2 | Replace Components | ME sub-team | N/A | 2 | 2 | 1 | 4 | 0% | 2 | 0%
DR - | 4 | b |  |  | Ultimate failure (bending) | Weakening of overall track structure |  |  |  | 1 | 4 | 1 | 4 | 1 | Replace Components | ME sub-team | N/A | 1 | 4 | 1 | 4 | 0% | 1 | 0%
DR - | 4 | [8 empty] | Item RPN & PV |  |  | 44 | 3 |  |  |  | Item RPN & PV |  |  | 44 | 0% | 3 | 0%
DR - | 5 | a | Treads | Move Tracks | Treads separate | Failure to Drive | Loss of tread connection pins |  | Device Testing | 1 | 8 | 1 | 8 | 1 | Replace connection pins | ME sub-team | N/A | 1 | 8 | 1 | 8 | 0% | 1 | 0%
DR - | 5 | b |  |  | Treads jammed |  | Regolith simulant inside tread joints |  |  | 4 | 8 | 3 | 96 | 12 | Clean treads | ME sub-team | Treads cleaned | 2 | 8 | 5 | 80 | 16.67% | 10 | 16.67%
DR - | 5 | c |  |  | Skip teeth on sprockets |  | Regolith simulant inside |  |  | 4 | 8 | 3 | 96 | 12 | Clean treads | ME sub-team | Treads cleaned; treads modified; brushes implemented on inside of tracks | 5 | 8 | 5 | 200 | -108.3% | 25 | -108.3%
DR - | 5 | [8 empty] | Item RPN & PV |  |  | 200 | 25 |  |  |  | Item RPN & PV |  |  | 288 | -44% | 36 | -44%
DR - | 6 | a | Support Plates | Support Load | Yielding failure | Warping of overall track structure | Overload |  |  | 2 | 3 | 1 | 6 | 2 | Replace Components | ME sub-team | N/A | 2 | 3 | 1 | 6 | 0% | 2 | 0%
DR - | 6 | b |  |  | Ultimate failure (tearing) | Weakening of overall track structure |  |  |  | 1 | 5 | 1 | 5 | 1 | Replace Components | ME sub-team | N/A | 1 | 5 | 1 | 5 | 0% | 1 | 0%
DR - | 6 | c |  |  |  | Loss of track function |  |  |  | 1 | 8 | 1 | 8 | 1 | Replace Components | ME sub-team | N/A | 1 | 8 | 1 | 8 | 0% | 1 | 0%
DR - | 6 | d |  | Connect / support track components | Yielding failure | Warping of overall track structure |  |  |  | 2 | 3 | 1 | 6 | 2 | Replace Components | ME sub-team | N/A | 2 | 3 | 1 | 6 | 0% | 2 | 0%
DR - | 6 | e |  |  | Ultimate failure (tearing) | Loss of track function |  |  |  | 1 | 8 | 1 | 8 | 1 | Replace Components | ME sub-team | N/A | 1 | 8 | 1 | 8 | 0% | 1 | 0%
DR - | 6 | [8 empty] | Item RPN & PV |  |  | 33 | 7 |  |  |  | Item RPN & PV |  |  | 33 | 0% | 7 | 0%
DR - | 7 | a | Supports | Provide rigid connection between right and left tracks | Yielding failure | Tracks out of square; device does not drive straight | Bending stress due to turning | Safety factors > 1.5 for supports | Device Testing | 3 | 5 | 2 | 30 | 6 | Replace Components | ME sub-team | N/A | 3 | 5 | 2 | 30 | 0% | 6 | 0%
DR - | 7 | b |  |  | Ultimate failure (bending) | Reduced control of track locomotion |  |  |  | 2 | 6 | 1 | 12 | 2 | Replace Components | ME sub-team | N/A | 2 | 6 | 1 | 12 | 0% | 2 | 0%
DR - | 7 | c |  |  |  | Loss of track locomotion |  |  |  | 2 | 8 | 1 | 16 | 2 | Replace Components | ME sub-team | N/A | 2 | 8 | 1 | 16 | 0% | 2 | 0%
DR - | 7 | [8 empty] | Item RPN & PV |  |  | 58 | 10 |  |  |  | Item RPN & PV |  |  | 58 | 0% | 10 | 0%
DR - | 8 | a | Scoop | Move obstacles | Operator error | Damage to underside of device | Camera malfunction | Practice under competition-simulated conditions |  | 5 | 4 | 5 | 100 | 25 | Replace / repair camera(s) and/or damaged components; more practice | ME sub-team | N/A | 5 | 4 | 5 | 100 | 0% | 25 | 0%
DR - | 8 | b |  |  |  |  | Insufficient practice |  |  | 7 | 4 | 5 | 140 | 35 | Replace / repair damaged components | ME sub-team | N/A | 7 | 4 | 5 | 140 | 0% | 35 | 0%
DR - | 8 | c |  |  |  | Device immobilization | Camera malfunction | Practice under competition-simulated conditions |  | 5 | 7 | 1 | 35 | 5 | Replace / repair camera(s); more practice; perform maneuvers to mobilize device | ME sub-team | N/A | 5 | 4 | 1 | 20 | 42.86% | 5 | 0%
DR - | 8 | d |  |  |  |  | Insufficient practice |  |  | 7 | 7 | 1 | 49 | 7 | Perform maneuvers to mobilize device | ME sub-team | N/A | 7 | 4 | 1 | 28 | 42.86% | 7 | 0%
DR - | 8 | e |  |  | Functional subsystem failure | Damage to subsystem | Insufficient scoop component strength |  |  | 7 | 6 | 1 | 42 | 7 | Repair / replace subsystem components | ME sub-team | N/A | 7 | 6 | 1 | 42 | 0% | 7 | 0%
DR - | 8 | f |  |  | Functional subsystem failure | Device immobilization | Insufficient motor (linear actuator) strength |  |  | 3 | 7 | 1 | 21 | 3 | Perform maneuvers to mobilize device | ME sub-team | N/A | 3 | 4 | 1 | 12 | 42.86% | 3 | 0%
DR - | 8 | [8 empty] | Item RPN & PV |  |  | 387 | 82 |  |  |  | Item RPN & PV |  |  | 342 | 11.63% | 82 | 0%
[22 empty] | 22.47% |  | 20.4%

## FMECA Scoop (Dig)
Failure Mode, Effects, and Criticality Analysis (FMECA) of Scoop Sub-System
[9 empty] | FMECA No. | [5 empty] | ME-DI-1
|  |  | Sub-system: | Scoop |  |  | P = Probability of Occurrence |  | Final Design Deadline: | [5 empty] | 2010-05-03
|  |  | System: | A.R.T.E.M.I.S. PRIME Lunar Excavator |  |  | S = Severity of Failure Effect |  | Prepared by: | [5 empty] | Amanda Huff
|  |  | Design Responsibility: | ME Sub-Team: C. Gries, A. Huff, W. Tyree |  |  | D = Probability of Detection |  | FMEA Date (Orig.) | [5 empty] | 2010-05-18
[7 empty] | RPN = Risk Priority Number |  | FMEA Date (Rev.) | [5 empty] | 2010-07-24
Assessment Number |  |  | Component / Subsystem Name | Function | Potential Failure Mode(s) | Potential Effect(s) of Failure | Potential Cause(s) / Mechanisms of Failure | Current Controls (Prevention) | Current Controls (Detection) | Risk Assessment |  |  |  |  | Recommended Action(s) | Responsibility | Action(s) Taken | Revised Risk Assessment
[10 empty] | P | S | D | RPN | PV |  |  |  | P | S | D | RPN | % RPN Reduction | PV | % PV Reduction
DI - | 1 | a.1 | Control System (Wiring) | Control linear actuator | Device not actuated | Failure to lift | No power due to faulty electrical connections | Supervision / review by advisor proir to implementation of electrical control system | Device testing | 4 | 7 | 4 | 112 | 16 | Repair Connections | EE sub-team | Connections repaired prior to competition | 2 | 7 | 4 | 56 | 50% | 8 | 50%
DI - | 1 | a.2 | (Wiring) |  |  |  | Failure to execute desired function due to faulty electrical connections |  |  | 5 | 7 | 5 | 175 | 25 | Repair Connections | EE sub-team | Connections repaired prior to competition | 2 | 7 | 5 | 70 | 60% | 10 | 60%
DI - | 1 | a | [7 empty] | Item RPN & PV |  |  | 287 | 41 |  |  |  | Item RPN & PV |  |  | 126 | 56.1% | 18 | 56.1%
DI - | 1 | b | (Battery) | Control linear actuator |  |  | No power due to battery charger malfunction |  | Monitor charging battery | 2 | 7 | 5 | 70 | 10 | Rectify charger issue; charge battery | EE sub-team | N/A | 2 | 7 | 5 | 70 | 0% | 10 | 0%
DI - | 1 | c | (Code) |  |  |  | Failure to execute desired function due to incorrect code (progamming issue) | Supervision / review by advisor proir to implementation of electrical control system | Device testing | 5 | 7 | 5 | 175 | 25 | Revise Code | EE sub-team | Code revised prior to competition | 1 | 7 | 5 | 35 | 80% | 5 | 80%
DI - | 1 | d | (Interface) |  |  |  | Mistake by operator at human-machine interface (HMI) | Practice under competition-simulated conditions | Observaton (during device testing / practice) | 6 | 1 | 1 | 6 | 6 | Continued Practice | C. Gries | Gries practiced both at WKU and at Kennedy as able | 2 | 1 | 1 | 2 | 66.67% | 2 | 66.67%
DI - | 1 | e | (Sabertooth 2x25 Motor Controller) |  | Correct commands not sent to motor | Failure to lift | Motor controller fault | Supervision / care taken during operation | Device testing | 4 | 7 | 1 | 28 | 4 | Replace / repair controller. Determine cause of fault and take action to prevent recurrence | EE sub-team | N/A | 5 | 7 | 1 | 35 | -25% | 5 | -25%
DI - | 1 | f | (CSD Controller Board) | Command motor controller | Correct commands not sent to motor controller | Failure to lift | Controller board fault | Supervision / care taken during operation | Device testing | 4 | 7 | 1 | 28 | 4 | Replace / repair board. Determine cause of fault and take action to prevent recurrence | EE sub-team | Board replaced prior to competition | 6 | 7 | 1 | 42 | -50% | 6 | -50%
DI - | 1 | [8 empty] | Electrical RPN & PV |  |  | 594 | 90 |  |  |  | Electrical RPN & PV |  |  | 310 | 47.81% | 46 | 48.89%
DI - | 2 | a | Linear Actuator | Lift Scoop | Functional Device Failure | Failure to lift | Overload | Derating of linear actuator | Device Testing | 3 | 8 | 2 | 48 | 6 | Repair device; decrease load; if necessary purchase new device with higher load rating | EE sub-team; ME sub-team | (Device Tested) | 2 | 8 | 2 | 32 | 33.33% | 4 | 33.33%
DI - | 2 | b |  |  |  |  | Fatigue |  |  | 1 | 8 | 3 | 24 | 3 | Repair device; decrease load; if necessary purchase new device with higher load rating |  | (Device Tested) | 1 | 8 | 3 | 24 | 0% | 3 | 0%
DI - | 2 | [8 empty] | Item RPN & PV |  |  | 72 | 9 |  |  |  | Item RPN & PV |  |  | 56 | 22.22% | 7 | 22.22%
DI - | 3 | a | Turning Arms | Turn Scoop | Loss of connection pins | Failure to turn scoop to desired position | Set Screw Failure |  | Device testing | 5 | 7 | 1 | 35 | 5 | Repair or redesign securing mechanism | ME sub-team | Replaced set screws with socket head cap screws | 1 | 7 | 1 | 7 | 80% | 1 | 80%
DI - | 3 | b |  |  | Loss of bushings |  |  |  |  | 5 | 3 | 1 | 15 | 5 | Repair or redesign securing mechanism | ME sub-team | Replaced set screws with socket head cap screws | 1 | 3 | 1 | 3 | 80% | 1 | 80%
DI - | 3 | c |  |  |  |  | Insufficient press fit |  |  | 5 | 3 | 1 | 15 | 5 | None | ME sub-team | Re-set bushings prior to competition | 2 | 3 | 1 | 6 | 60% | 2 | 60%
DI - | 3 | d |  |  | Yielding failure of bushings |  | Insufficient component strength | Derating of Bushings |  | 1 | 3 | 1 | 3 | 1 | Purchase of sufficient components | ME sub-team | N/A | 1 | 3 | 1 | 3 | 0% | 1 | 0%
DI - | 3 | e |  |  | Yielding of scoop sides |  |  | Stress vs. strength modeling |  | 1 | 4 | 1 | 4 | 1 | Redesign; repair or fabricate | ME sub-team | N/A | 1 | 4 | 1 | 4 | 0% | 1 | 0%
DI - | 3 | f |  |  | Tearing of scoop sides | Failure to turn scoop |  |  |  | 1 | 8 | 1 | 8 | 1 | Redesign; repair or fabricate | ME sub-team | N/A | 1 | 8 | 1 | 8 | 0% | 1 | 0%
DI - | 3 | g |  |  | Unstable turning motion | Failure to turn scoop to desired position | Unstable connections between scoop sides and turning arms |  |  | 7 | 2 | 1 | 14 | 7 | Increase thickness of scoop at turning arm connections | ME sub-team | Riveted pieces of sheet metal to scoop sides at turning arm connections | 3 | 2 | 1 | 6 | 57.14% | 3 | 57.14%
DI - | 3 | [8 empty] | Item RPN & PV |  |  | 94 | 25 |  |  |  | Item RPN & PV |  |  | 37 | 60.64% | 10 | 60%
DI - | 4 | a | Lifting Arms | Lift Scoop | Yielding of lifting arms at critical points | Failure to lift scoop to desired position | Insufficient component strength | Stress vs. strength modeling | Device testing | 5 | 5 | 1 | 25 | 5 | Redesign; repair or fabricate | ME sub-team | (Device Tested) | 3 | 5 | 1 | 15 | 40% | 3 | 40%
DI - | 4 | b |  |  | Yielding of scoop sides |  |  |  |  | 2 | 5 | 1 | 10 | 2 | Redesign; repair or fabricate | ME sub-team | (Device Tested) | 1 | 5 | 1 | 5 | 50% | 1 | 50%
DI - | 4 | c |  |  | Ultimate failure of lifting arms at critical points | Failure to lift scoop |  |  |  | 3 | 8 | 1 | 24 | 3 | Redesign; repair or fabricate | ME sub-team | (Device Tested) | 2 | 8 | 1 | 16 | 33.33% | 2 | 33.33%
DI - | 4 | d |  |  | Tearing of scoop sides |  |  |  |  | 1 | 8 | 1 | 8 | 1 | Redesign; repair or fabricate | ME sub-team | (Device Tested) | 1 | 8 | 1 | 8 | 0% | 1 | 0%
DI - | 4 | e |  |  | Unstable lifting motion | Failure to lift scoop to desired position | Unstable connections betweed scoop sides and lifting arms |  |  | 7 | 2 | 1 | 14 | 7 | Increase thickness of scoop at lifting arm connections | ME sub-team | Riveted pieces of sheet metal to scoop sides at lifting arm connections | 3 | 2 | 1 | 6 | 57.14% | 3 | 57.14%
DI - | 4 | [8 empty] | Item RPN & PV |  |  | 81 | 18 |  |  |  | Item RPN & PV |  |  | 50 | 38.27% | 10 | 44.44%
DI - | 5 | a | Support Brace | Bear load due to forces of single linear actuator | Yielding of support brace | Failure to bear forces and bending moments | Insufficient component strength | Stress vs. strength modeling;"skinning" of brace | Device testing | 6 | 4 | 1 | 24 | 6 | Redesign; repair or fabricate | ME sub-team | N/A | 2 | 4 | 1 | 8 | 66.67% | 2 | 66.67%
DI - | 5 | b |  |  | Ultimate failure of support brace |  |  |  |  | 5 | 6 | 1 | 30 | 5 | Redesign; repair or fabricate | ME sub-team | N/A | 1 | 6 | 1 | 6 | 80% | 1 | 80%
DI - | 5 | [8 empty] | Item RPN & PV |  |  | 54 | 11 |  |  |  | Item RPN & PV |  |  | 14 | 74.07% | 3 | 72.73%
DI - | 6 | a | Scoop | Dig Regolith | Bending of teeth | Inefficient Excavation | Insufficient teeth sheet metal strength | Reinforcement of teeth with thicker sheet metal | Device testing | 4 | 4 | 1 | 16 | 4 | Redesign; repair or fabricate | ME sub-team | (Device Tested) | 2 | 4 | 1 | 8 | 50% | 2 | 50%
DI - | 6 | b |  | Contain Regolith | Deformation of scoop | Loss of regolith | Insufficient scoop shell strength | Added support in center of scoop | Device testing | 1 | 4 | 1 | 4 | 1 | Redesign; repair or fabricate | ME sub-team | (Device Tested) | 1 | 4 | 1 | 4 | 0% | 1 | 0%
DI - | 6 | c |  |  | Tearing at weld | Loss of regolith | Insufficient weld strength | Reinforcement at welds |  | 2 | 5 | 1 | 10 | 2 | Redesign; repair or fabricate | ME sub-team | (Device Tested) | 1 | 5 | 1 | 5 | 50% | 1 | 50%
DI - | 6 | [8 empty] | Item RPN & PV |  |  | 30 | 7 |  |  |  | Item RPN & PV |  |  | 17 | 43.33% | 4 | 42.86%
[22 empty] | 42.81% |  | 43.4%

## FMECA ConveyorHopper (Deposit)
Failure Mode, Effects, and Criticality Analysis (FMECA) of Tracks Sub-System
[9 empty] | FMCEA No. | [5 empty] | ME-DE-1
|  |  | Sub-system: | Conveyor / Hopper |  |  | P = Probability of Occurrence |  | Final Design Deadline: | [5 empty] | 2010-05-10
|  |  | System: | A.R.T.E.M.I.S. PRIME Lunar Excavator |  |  | S = Severity of Failure Effect |  | Prepared by: | [5 empty] | Amanda Huff
|  |  | Design Responsibility: | ME Sub-Team: C. Gries, A. Huff, W. Tyree |  |  | D = Probability of Detection |  | FMEA Date (Orig.) | [5 empty] | 2010-05-18
[7 empty] | RPN = Risk Priority Number |  | FMEA Date (Rev.) | [5 empty] | 2010-07-23
Assessment Number |  |  | Component / Subsystem Name | Function | Potential Failure Mode(s) | Potential Effect(s) of Failure | Potential Cause(s) / Mechanisms of Failure | Current Controls (Prevention) | Current Controls (Detection) | Risk Assessment |  |  |  |  | Recommended Action(s) | Responsibility | Action(s) Taken | Revised Risk Assessment
[10 empty] | P | S | D | RPN | PV |  |  |  | P | S | D | RPN | % RPN Reduction | PV | % PV Reduction
DE - | 1 | a.1 | Control System (Wiring) | Control conveyor motor | Device not actuated | Failure to lift | No power due to faulty electrical connections | Supervision / review by advisor proir to implementation of electrical control system | Device testing | 4 | 7 | 4 | 112 | 16 | Repair Connections | EE sub-team | Connections repaired prior to competition | 2 | 7 | 4 | 56 | 50% | 8 | 50%
DE - | 1 | a.2 | (Wiring) |  |  |  | Failure to execute desired function due to faulty electrical connections |  |  | 5 | 7 | 5 | 175 | 25 | Repair Connections | EE sub-team | Connections repaired prior to competition | 2 | 7 | 5 | 70 | 60% | 10 | 60%
DE - | 1 | a | [7 empty] | Item RPN & PV |  |  | 287 | 41 |  |  |  | Item RPN & PV |  |  | 126 | 56.1% | 18 | 56.1%
DE - | 1 | b | (Battery) | Control conveyor motor |  |  | No power due to battery charger malfunction |  | Monitor charging battery | 2 | 7 | 5 | 70 | 10 | Rectify charger issue; charge battery | EE sub-team | N/A | 2 | 7 | 5 | 70 | 0% | 10 | 0%
DE - | 1 | c | (Code) |  |  |  | Failure to execute desired function due to incorrect code (progamming issue) | Supervision / review by advisor proir to implementation of electrical control system | Device testing | 5 | 7 | 5 | 175 | 25 | Revise Code | EE sub-team | Code revised prior to competition | 1 | 7 | 5 | 35 | 80% | 5 | 80%
DE - | 1 | d | (Interface) |  |  |  | Mistake by operator at human-machine interface (HMI) | Practice under competition-simulated conditions | Observaton (during device testing / practice) | 6 | 1 | 1 | 6 | 6 | Continued Practice | C. Gries | Gries practiced both at WKU and at Kennedy as able | 2 | 1 | 1 | 2 | 66.67% | 2 | 66.67%
DE - | 1 | e | (Sabertooth 2x25 Motor Controller) |  | Correct commands not sent to motor | Failure to lift | Motor controller fault | Supervision / care taken during operation | Device testing | 4 | 7 | 1 | 28 | 4 | Replace / repair controller. Determine cause of fault and take action to prevent recurrence | EE sub-team | N/A | 5 | 7 | 1 | 35 | -25% | 5 | -25%
DE - | 1 | f | (CSD Controller Board) | Command motor controller | Correct commands not sent to motor controller | Failure to lift | Controller board fault | Supervision / care taken during operation | Device testing | 4 | 7 | 1 | 28 | 4 | Replace / repair board. Determine cause of fault and take action to prevent recurrence | EE sub-team | Board replaced prior to competition | 6 | 7 | 1 | 42 | -50% | 6 | -50%
DE - | 1 | [8 empty] | Electrical RPN & PV |  |  | 594 | 90 |  |  |  | Electrical RPN & PV |  |  | 310 | 47.81% | 46 | 48.89%
DE - | 2 | a | Conveyor motor | Turn Conveyor | Functional Device Failure (motor stalls) | Failure to convey simulant | Overload (or atypical load conditions) | Derating of motors, gear reduction | Device Testing | 5 | 7 | 4 | 140 | 20 | Repair motor(s); decrease load; if necessary purchase new motors with increased power capabilities | EE sub-team; ME sub-team | (Changes made prior to competition increased the number of unknowns associated with the load distribution) | 7 | 7 | 4 | 196 | -40% | 28 | -40%
DE - | 2 | b |  |  |  |  | Fatigue |  |  | 2 | 7 | 4 | 56 | 8 | Repair motor(s); decrease load; if necessary purchase new motors with increased power capabilities | EE sub-team; ME sub-team | (Device Tested) | 2 | 7 | 4 | 56 | 0% | 8 | 0%
DE - | 2 | c |  |  |  |  | Not enough voltage supplied |  |  | 6 | 7 | 3 | 126 | 18 | Determine cause and take action to prevent recurrence | EE sub-team | None (unable to determine cause before competition) | 7 | 7 | 3 | 147 | -16.67% | 21 | -16.67%
DE - | 2 | [8 empty] | Item RPN & PV |  |  | 322 | 46 |  |  |  | Item RPN & PV |  |  | 399 | -23.91% | 57 | -23.91%
DE - | 3 |  | Gear reduction | Reduce speed, increase torque | Belt jumping teeth | Belt wear (decreased performance; eventual loss of conveyor function) | Loose belt | Belt tensioning | Device testing | 7 | 4 | 1 | 28 | 7 | Repair / re-tension belt | ME sub-team | Implemented improved belt tensioning system | 3 | 4 | 1 | 12 | 57.14% | 3 | 57.14%
DE - | 4 |  | Conveyor Sprockets | Turn conveyor | Wear | Performance degradation | Regolith simulant inside conveyor | Sealing the conveyor | Device Testing | 5 | 4 | 1 | 20 | 5 | Replace components; clean out conveyor periodically | ME sub-team | N/A | 5 | 4 | 1 | 20 | 0% | 5 | 0%
DE - | 5 | a | Conveyor Chain | Convey regolith simulant | Loss of simulant | Regolith inside conveyor, wear | Diminishing sealant adhesion quialities over time | Replace tape periodically | Device testing | 5 | 4 | 1 | 20 | 5 | Replace tape | ME sub-team | Tape replaced days before competition; change in chain structure / taping regime | 3 | 4 | 1 | 12 | 40% | 3 | 40%
DE - | 5 | b |  |  | (Multiple) cleats break | Failure to convey (some) simulant | Overload (or atypical load conditions) |  |  | 1 | 6 | 1 | 6 | 1 | Replace cleats | ME sub-team | N/A | 2 | 6 | 1 | 12 | -100% | 2 | -100%
DE - | 5 | c |  |  | Links separate |  | Atypical load conditions |  |  | 3 | 6 | 1 | 18 | 3 | Reduce load on chain (modify hopper / reduce load per trip) | ME sub-team | None (difficult to detect / unable to make changes in time for copmpetition) | 3 | 6 | 1 | 18 | 0% | 3 | 0%
DE - | 5 | d |  |  | Conveyor doesn't turn | Failure to convey simulant | Insufficient rigidity |  |  | 1 | 7 | 1 | 7 | 1 |  | ME sub-team | (Changes made prior to competition increased the number of unknowns associated with the load distribution) | 6 | 7 | 1 | 42 | -500% | 6 | -500%
DE - | 5 | [8 empty] | Item RPN & PV |  |  | 92 | 21 |  |  |  | Item RPN & PV |  |  | 74 | 19.57% | 16 | 23.81%
DE - | 6 |  | Wear Strips | Protect against conveyor chain wear | Wear | Wear of conveyor chain | Regolith simulant between chain and strip | Clean out conveyor periodically |  | 5 | 3 | 1 | 15 | 5 | Replace wear strips | ME sub-team | N/A | 5 | 3 | 1 | 15 | 0% | 5 | 0%
DE - | 7 | a | Conveyor Structure | Connect / provide stability for conveyor components | Conveyor collapses | Failure to convey simulant | Loss of connectors (bolts / nuts) | Check / tighten connections periodically | Device testing | 6 | 7 | 1 | 42 | 6 | Reassemble conveyor | ME sub-team | Connectors inspected prior to competition | 2 | 7 | 1 | 14 | 66.67% | 2 | 66.67%
DE - | 7 | b |  |  | Yielding Failure |  | Insufficient strength | Safety factor >>1.5 for structure |  | 1 | 8 | 1 | 8 | 1 | Acquire and replace damaged components | ME sub-team | N/A | 1 | 8 | 1 | 8 | 0% | 1 | 0%
DE - | 7 | c |  |  | Ultimate Failure |  | Insufficient strength | Safety factor >>1.5 for structure |  | 1 | 8 | 1 | 8 | 1 | Acquire and replace damaged components | ME sub-team | N/A | 1 | 8 | 1 | 8 | 0% | 1 | 0%
DE - | 7 | [8 empty] | Item RPN & PV |  |  | 73 | 13 |  |  |  | Item RPN & PV |  |  | 45 | 38.36% | 9 | 30.77%
DE - | 8 | a | Hopper | Contain collected simulant | Ultimate failure (tearing) | Loss of simulant (major) | Overload |  | Device testing | 2 | 6 | 1 | 12 | 2 | Repair / replace hopper | ME sub-team | (Device Tested) | 1 | 6 | 1 | 6 | 50% | 1 | 50%
DE - | 8 | b |  |  | Formation of gaps in hopper structure | Loss of simulant | Overload |  |  | 2 | 4 | 1 | 8 | 2 | Add reinforcement struts | ME sub-team | Reinforcement struts with high sectional modulus incorporated into hopper floor; device tested | 1 | 4 | 1 | 4 | 50% | 1 | 50%
DE - | 8 | c |  |  | Substantial volume of excavated simulant leaked | Loss of simulant (moderate) | Inadequate connection at joints | Chaulking |  | 5 | 3 | 1 | 15 | 5 | Chaulk separation points | ME sub-team | (Device Tested) | 2 | 3 | 1 | 6 | 60% | 2 | 60%
DE - | 8 | d |  |  |  |  | Inadequate connection at pop rivet holes |  |  | 3 | 3 | 1 | 9 | 3 | Chaulk separation points | ME sub-team | (Device Tested) | 2 | 3 | 1 | 6 | 33.33% | 2 | 33.33%
DE - | 8 | e |  |  | Deformation of hopper | Some simulant not directed to conveyor; amount of deposited regolith simulant reduced | Overload |  |  | 8 | 2 | 3 | 48 | 24 | Add reinforcement struts | ME sub-team | Reinforcement struts with high sectional modulus incorporated into hopper floor | 2 | 2 | 3 | 12 | 75% | 6 | 75%
DE - | 8 | f |  |  | Simulant "sticking" to angled hopper floor |  | Insufficient hopper floor angle; lack of vibration of hopper floor; high coefficient of friction between hopper floor and regolith simulant |  |  | 8 | 5 | 1 | 40 | 8 | Increase hopper floor angle; introduce vibration into the hopper floor; modify hopper floor to reduce coefficient of friction | ME sub-team | False bottom incorporated to increase floor angle (resting on floor reinforcers); false bottom constrained minimally in order to allow floor vibration (due to overall device movement / vibration) | 4 | 5 | 1 | 20 | 50% | 4 | 50%
DE - | 8 | [8 empty] | Item RPN & PV |  |  | 132 | 44 |  |  |  | Item RPN & PV |  |  | 54 | 59.09% | 16 | 63.64%
DE - | 9 | a | Hopper / Conveyor Connection | Facilitate transfer of simulant from hopper to conveyor | Separation of hopper from conveyor | Failure to convey simulant | Loss of connectors (bolts / nuts) | Check / tighten connections periodically | Device testing | 6 | 7 | 1 | 42 | 6 | Reassemble conveyor | ME sub-team | Connectors inspected prior to competition | 2 | 7 | 1 | 14 | 66.67% | 2 | 66.67%
DE - | 9 | b |  |  |  |  | Failure of hopper connection (shear) | Minimization of shear forces at hopper / conveyor connection |  | 2 | 8 | 1 | 16 | 2 | Repair / replace hopper | ME sub-team | (Device Tested) | 1 | 8 | 1 | 8 | 50% | 1 | 50%
DE - | 9 | c |  |  | Escape of simulant into conveyor | Regolith inside conveyor, wear; amount of deposited regolith simulant reduced | Gaps in conveyor exposed to simulant | Incorporation of rubber flaps and foam padding at exposed site |  | 3 | 6 | 2 | 36 | 6 | Replace / reposition flaps and foam | ME sub-team | Flaps and foam repositioned prior to competition | 3 | 6 | 2 | 36 | 0% | 6 | 0%
DE - | 9 | [8 empty] | Item RPN & PV |  |  | 94 | 14 |  |  |  | Item RPN & PV |  |  | 58 | 38.3% | 9 | 35.71%
DE - | 10 | a | Conveyor Supports | Support / constrain conveyor | Yielding failure | Increased device length (potential breach of design requirements) | Overload | Safety factors > 1.5 for supports | Device testing | 4 | 2 | 6 | 48 | 24 | Replace supports | ME sub-team | (Device Tested) | 1 | 2 | 6 | 12 | 75% | 6 | 75%
DE - | 10 | b |  |  |  | Increased stresses elsewhere in device |  |  |  | 4 | 2 | 6 | 48 | 24 | Replace supports | ME sub-team | (Device Tested) | 1 | 2 | 6 | 12 | 75% | 6 | 75%
DE - | 10 | c |  |  | Ultimate failure (bending) | Conveyor collapse |  |  |  | 3 | 8 | 1 | 24 | 3 | Replace supports | ME sub-team | (Device Tested) | 1 | 8 | 1 | 8 | 66.67% | 1 | 66.67%
DE - | 10 | d |  |  |  | Increased shear forces on hopper |  |  |  | 3 | 3 | 2 | 18 | 6 | Replace supports | ME sub-team | (Device Tested) | 1 | 3 | 2 | 6 | 66.67% | 2 | 66.67%
DE - | 10 | [8 empty] | Item RPN & PV |  |  | 138 | 57 |  |  |  | Item RPN & PV |  |  | 38 | 72.46% | 15 | 73.68%
[22 empty] | 38.47% |  | 38.59%